## Lists (hidden)
GTC 50-01 | R1 | 02 - Drilling | Draw Works | 5 1/2" | 2 7/8"
GTC 50-02 | R2 | 03 - Reaming | Mud Pump | 6" | 4 1/2"
GTC 50-03 | R3 | 04 - Coring | Kelly | 8 1/2" | 5"
GTC 100-01 | ILM | 05 - C&C | Rotary/PTO | 12 1/4" | 5 1/2"
GTC 100-02 |  | 06 - Tripping | Carrier Engine | 17 1/2" | 7"
GTC 100-03 |  | 07 - Lubrication | Compressor | 26" | 9 5/8"
GTC 100-04 |  | 08 - Breakdown | Drillograph |  | 13 3/8"
GTC 100-07 |  | 09 - Slip & Cut | Others |  | 20"
GTC 100-08 |  | 10 - Deviation Survey
GTC 150-02 |  | 11 - Logging
GTC 160-01 |  | 12 - Casing R/in
GTC 200-01 |  | 13 - Wait on Cement
GTC 250-01 |  | 14 - Nipple Up/Down BOP
GTC 1000-01 |  | 15 - Test BOP
GTC 1000-02 |  | 16 - Drill Stem BOP
17 - Plug Back
18 - Cementing
19 - Fishing
20 - Directional Work
21 - Tubing Job
22 - Testing LOT CIT
23 - Other

## DPR
GTC — Daily Progress Report (DPR)
RIG NO. | GTC 200-01 |  | DATE | 2026-06-10 |  |  |  | DRILLING SECTION |  |  |  | CASING SECTION
WELL NAME | OPERATION TASK CODE | WORK TYPE | START TIME | END TIME | TOTAL TIME (Auto) | DESCRIPTION / REMARKS | BREAKDOWN EQUIPMENT | DRILLING SECTION | FROM (M) | TO (M) | TOTAL (Auto) | CASING SECTION | FROM (M) | TO (M) | TOTAL (Auto)
LNMH | 02 - Drilling | R1 | 6:00 | 12:00 | 6 | CONTINUED DRILLING8 1/2" HOLE SECTION DRILL FROM 1950M TO 2001M (T/D COMPLTED) |  | 8-1/2" | 1950 | 2001 | 51
LNMH | 05 - C&C | R1 | 12:00 | 13:45 | 1.75 | PUMPED HI VISC PILL C&C MUD PRIOR TO WIPE TRIP FLOW CHECKED NEGATIVE. PUMP SLUG R / BACK KELLY.
LNMH | P/O | R1 | 13:45 | 18:00 | 4.25 | STARTED P/O FOM 2001M TO 1009M. DURING P/O OBSERVED SEVERE T/PULL FROM 1781M TO 1714M. CLEARED THE SAME BY MULTIPLE RECIPROCATION. INTERMITTENT TGHT PULL CLEARED BY RECIPROCATION. HOLE KEPT FILL WITH MUD AT ALL TIME (FP/O IIP) |  |  | 2001 | 1009 | -992
LNMH | P/O | R1 | 18:00 | 19:30 | 1.5 | CONTINUED P/O BIT FROM 1009M UPTO 588M (INSIDE SHOE) FILLUP HOLE WITH MUD AT ALL TIME. |  |  | 1009 | 588 | -421
LNMH | R/IN | R1 | 19:30 | 23:30 | 4 | START R/IN BIT FROM 588M TO 1989M. INERMITTENT HELD UP ZONES CLEARED BY RECIPROCATIONS. M/UP KELLY WASH DOWN FROM 1989M TO 2001M (BTM). |  |  | 588 | 1989 | 1401
LNMH | 05 - C&C | R1 | 23:30 | 1:45 | 2.25 | PUMPED HI-VISC PILL. C&C MUD PRIOR TO SHORT TRIP. FLOW CHECK FOUND NEGATIVE, PUMPED SLUG R/B KELLY.
LNMH | P/O | R1 | 1:45 | 3:45 | 2 | STARTED PULLOUT BIT FROM 2001M TI 1344M FREELY. HOLE KEPT FULL WITH MUD AT ALL TIMES. |  |  | 2001 | 1344 | -657
LNMH | R/IN | R1 | 3:45 | 6:00 | 2.25 | STARTED R/IN BIT FROM 1344M UPTO 1923M FREELY. FURTHER R/IN IIP. |  |  | 1344 | 1923 | 579
TOTAL |  |  |  |  | 24 | [5 empty] | -39 |  |  |  | 0